## WP1 Deliverables
WP1 DELIVERABLES
Activity | Deliverables | Topic (Content) | Media/Channels | Indicator target (n.) | LOCATION | DATE | Target groups
1.1 Day-to-day project management, coordination and internal communication | D1.1.1 Project GANTT | This deliverable will include the timeline of the activities, milestones and output delivery deadlines | project website | 1 | Venice | by July 2022 (Responsible PPs: LP) | PPs
| D1.1.2 WPs flow chart | This deliverable will facilitate contacts between PPs in order to build cross-border working groups that will cooperate in the implementation of activities | project website | 1 | Venice | by July 2022 (Responsible PPs: LP) | PPs
| D1.1.3 Common platform | This platform will be used to store and share as well as to work on common documents while tracking changes made by each member of a project working group | project website | 1 | Venice | by July 2022 (Responsible PPs: LP) | PPs
| D1.1.4 Minutes of the kick-off meeting |  | project website | 1 | Venice | by July 2022 (Responsible PPs: LP) | PPs
| D1.1.5 Minutes of the no. 3 PSC meetings |  | project website | 1 | Venice | in July 2022, January 2023 and June 2023 (Responsible PPs: LP) | PPs
| D1.1.6 Minutes of the on-line working meetings |  | project website | 1 | Venice | one week after each on-line meeting (Responsible PPs: LP) | PPs
| D1.1.7 Monitoring and evaluation plan | This deliverable will facilitate to keep the project in-line with the time plan | project website | 1 | Venice | by July 2022 (Responsible PPs: LP) | PPs
| D1.1.8 Report on the project closure |  | project website | 1 | Venice | by July 2023 (Responsible PPs: LP) | PPs
1.2 Financial management | D1.2.1 Periodical financial progress reports |  | SIU | 2 (for each PP) | Venice | in January 2023 and July 2023 (Responsible PPs: LP with the contribution of each PP) | PPs and JS
| D1.2.2 Financial statements |  | SIU | 2 (for each PP) | Venice | in January 2023 and July 2023 (Responsible PPs: LP with the contribution of each PP) | PPs and JS

## Communication Strategy (WP2)
SECURE COMMUNICATION STRATEGY - PLAN (WP2)
Activity | Deliverables | Topic (Content) | Media/Channels | Indicator target (n.) | LOCATION | DATE | Target groups
2.1 Online and offline events | D2.1.1 Kick-off event report (documentation including, e.g., invitation, posters, mailing list, participants, presentations, audio/video records) | Kick off event A summary of the event that will be held, elaborating the agenda and the speakers with a short description of the project and the partnership. | web page and facebook of the project and project partners, press releases, email | 1 | Venice | June 2022 (Responsible PPs: LP, PP2) | General public,local, regional and national public authorities and related entities, universities and research institutes, other project partners in different Interreg programmes in the same topic
| D2.1.2 Documentation related to visit tours carried out, e.g. dates, participants, activities undertaken, discussions, suggestions, addresses for further contacts) | Local Meetings (in presence) Info day/visit in the pilot sites will be organised to show and present the solutions proposed by the project and think to transfer the main concepts in other areas. This activity will ensure the transfer of the project outcomes from the cluster to end users, e.g. farmers and stakeholders in coastal areas of the Adriatic basin. The point of those events is to motivate target groups to take active role in project implementation | web page and facebook of the project and project partners, press releases, email | 2 (1 IT & 1 CR) | Neretva coast and Venice coast | October 2022 in Croatia (Responsible PP: PP4); Spring 2023 in the Venice coastland (Responsible PPs:LP, PP2) | General public, local, regional and national public authorities and related entities, education and training centers, universities and research institutes
| D2.1.3 Final high-level event (documentation including, e.g., invitation, posters, mailing list, participants, presentations, audio/video records) | An high-level event will close the communication activities at the end of the project. All results of project activities will be presented | web page and facebook of the project and project partners, press releases, email | 1 | Padova | June 2023 (Responsible PPs: LP, PP1) | General public, local, regional and national public authorities and related entities, education and training centers and universities and research institutes
| D2.1.4 Participation in events with Programme and other ETC Adriatic Programmes, EUSAIR Steering Groups, EU institutions. | Exchange of expertise with other EU projects focused on management of lowlying coastlands (off-line or hybrid) | web page and facebook of the project | 2 | depending on EU Programmes | depending on calls by JS (all PPs) | Education and training centers and universities and research institutes
2.2 Promotional campaigns and media relations | D2.2.1 Promotional campaign communication plan | A plan with the promotional activities will be put in place to raise awareness about the salinization process in lowlying coastal environments, specifically in relation to the effects on farmland productivity and biodiversity, and promote a proper management strategies | web page and facebook of the project, questionnaire | 1 | - | July 2022 (Responsible PPs: PP2, PP4) | General public,local, regional and national public authorities and related entities, universities and research institutes, other project partners in different Interreg programmes in the same topic
| D2.2.2 Project poster placed at a location visible to the public in each PP headquarter | Highlighting the SeCure project in the PP offices | - | 1 | Padova, Venice, Split, Dubrovnik, Zagreb | soon (all PPs) | General public visiting the PP headquarters (local stakeholders, water and land managers, technicians of the local and regional authorities, students, researchers)
| D2.2.3 Roll-up to be exposed during the project events | Highlighting the SeCure project in project events | - | 1 | Padova, Venice, Split, Dubrovnik, Zagreb | once the communication kit will be made available by the JS (Responsible PPs: LP and PP3) | General public
| D2.2.4 Addition of SeCure project name/acronym to the permanet plaque placed in the monitoring networks and small infrastructures established during the MAC IT-HR projects | Highlighting the SeCure project in the pilot sites | - | 2 (1 IT site & 1 CR site) | Venice and Neretva coastlands | once the communication kit will be made available by the JS (Responsible PPs: PP1, PP3) | General public living & working in the farmland
| D2.2.5 Promotional material for secondary & high schools | A key target group for the promotional campaign will be young generations, in agreement with the Next Gen EU plan. In this respect, material will be sent to secondary and high schools of the regions facing the Adriatic Sea where SeCure will develop its activities. Moreover, on-line and in-person lectures will be proposed, by email contacts with the professors teaching scientific topics in the various schools | digital material (ppt), factsheets, hybrid lectures, email | 2 (factsheets - 1 IT & 1 CR) 2 (ppts - 1 IT & 1 CR) 2 (hybrid lectures - 1 IT & 1 CR) | Veneto region and Neretva plain | by the end of the project (Responsible PPs: LP, PP1, PP3) | The key target group for the promotional campaign will be young generations, in agreement with the Next Gen EU plan
| D2.2.6 Press releases | Highlighting the SeCure project and its outcomes | local and/or regional and/or national newspapers, radios, TV | 2 (1 IT & 1 CR) |  | by June 2023 (Responsible PPs: PP2, PP5) | General public
| D2.2.7 Articles in (international) on-line magazines on SeCure outcomes [plus 4 scientific papers] | Summarizing the scientific and technical outcomes without using jargon so that it is understandable by technicians/educators/public from outside the specific discipline | # international magazines (e.g., Il Sole 24 Ore, Platinum, magaziens published by CW) # scientific journals | 2 (1 IT & 1 CR) 4 papers | Italy, Croatia, Europe | by June 2023 (Responsible PPs: LP, PP6) | General public, technical officers of regional authorities
| D2.2.8 (IT & HR) journalist on-site visits | Raising awareness about the salinization process in lowlying coastal environments, specifically in relation to the effects on farmland productivity and biodiversity, and promote a proper management strategies | local and/or regional and/or national newspapers, radios, TV | 2 (1 IT & 1 CR) | Venice coastland and Neretva plain | In concurrence with with activities of D2.1.2, i.e. in autumn 2022 in Croatia and in spring 2023 in Italy (Responsible PPs: PP2 (with the help of LP), PP4) | General public
| D2.2.9 Digital promotional campaigns on media |  |  | 1 |  | by July, after the meeting with JS (Reseponsible PPs: PP2) | General public
2.3 Digital and web-based activities | D2.3.1 Digital editorial plan |  |  | 1 |  | by July, after the meeting with JS (Reseponsible PPs: PP4) | General public
| D2.3.2 SeCure Website and social media. | They will contain the main project steps and outcomes (guidelines, mapping). They will be constantly updated to inform about the online and offline events and the promotional campaigns. | web page, facebook, researchgate | 1 | - | by July and then constantly updated (Responsible PPs: PP4 plus LP for Researchgate) | General public,local, regional and national public authorities and related entities, universities and research institutes, other project partners in different Interreg programmes in the same topic
| D2.3.3 Interviews and short videos | The project contents and results will be shown in a series of short videos (about 3 minutes each). Interviews with researchers and stakeholders will be carried out in concomitance with events organized by EU and ntional/local administration, such as "European Researchers' Night". SeCure cluster team will present the project via radio reports, TV sessions and newspapers; this way of dissemination corresponds to digital media use and enables the wide spread of the project presentation. | web page and facebook of the project and project partners; radio, TV, newspaper | 3 | Venice coastland and Neretva plain | by June 2023 (Responsible PPs: all PPs) | General public, stakeholders, local and regional public authorities and related entities
| D2.3.4 Smartphone App | App (1 IT & 1 HR) for the real-time monitoring of the salinization condition in the lowlying farmlands and water bodies within the project locations. | smartphone | 2 (1 IT & 1 CR with EN subtitles) | Venice coastland and Neretva plain | by June 2023 (Responsible PPs: LP, PP1 and PP3) | General public, stakeholders, local and regional public authorities and related entities

## WP3 Deliverables
WP3 DELIVERABLES
Activity | Deliverables | Topic (Content) | Media/Channels | Indicator target (n.) | LOCATION | DATE | Target groups
3.1 Exchange and exploitation of projects' results | D3.1.1 Exploitation plan covering for the knowledge arose from MAC IT-HR projects | Report summarizing the most important outcomes of the MAC IT-HR project outcomes about saltwater intrusion in a changing climate | project website | 1 | Northern and Central Adriatic coast | September 2022 (Responsible PPs: LP, PP1, PP3, PP5) | Local, regional and national public authorities and related entities, education and training centers, universities and research institutes
| D3.1.2 Technical report on the investigation on climate change, its effect to low laying coastal agricultural areas in Italian site and potential for the implementation to other vulnerable areas within the Adriatic basin | Report summarizing the most important outcomes of the SeCure outcome along th Italian coast | project website | 1 | Padova | by June 2023 (Responsible PPs: PP1 with the help of LP) | Local, regional and national public authorities and related entities, education and training centers, universities and research institutes
| D3.1.3 Technical report on the investigation on climate change, its effect to low laying coastal agricultural areas in Croatian site and potential for the implementation to other vulnerable areas within the Adriatic basin | Report summarizing the most important outcomes of the SeCure outcome along th Croatian coast | project website | 1 | Split | June 2023 (Responsible PPs: LP, PP1) | Local, regional and national public authorities and related entities, education and training centers, universities and research institutes
| D3.1.4 Short, high quality video on results, measures and adaptation plans features |  | web page and facebook of the project and project partners | 1 |  | by June 2023 (Responsible PPs: PP2 and PP5) | General public, local, regional and national public authorities and related entities
3.2 Contributions to the next programming period | D3.2.1 Project idea Nr.1. for the programme period 2021-2027 |  |  | 1 |  | by June 2023 (Responsible PPs: all PPs) | JS
| D3.2.2 Project idea Nr.2. for the programme period 2021-2027 |  |  | 1 |  | by June 2023 (Responsible PPs: all PPs) | JS
3.3 Awareness raising and engagement | D3.3.1 Study visit to Italian representative site | Shared visit between the partners | - | 1 | Venice coast | by June 2023 (Responsible PPs: PP2) | PPs, general public, local authorities
| D3.3.2 Study visit to Crotian representative site | Shared visit between the partners | - | 1 | Neretva coast | by June 2023 (Responsible PPs: all PP5 and PP6) | PPs, general public, local authorities
| D3.3.3 Study visit reports: field surveys to the project pilot sites |  | project website | 2 (1 IT & 1 CR) | - | by June 2023 (Responsible PPs: LP, PP3) | General public, local, regional and national public authorities and related entities
| D3.3.4 Thematic seminar on coastal salinization issues and adaptation state of the art |  | web page and facebook of the project and project partners | 1 | what about co-organizing a session at the next EGU ? | by June 2023 (Responsible PPs: LP, PP1, PP3, PP6) | Education and training centers and Universities and research institutes